## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/7 - 9/11 | - Set up project repository with version control (GitHub) - Drafted the Software Project Plan Proposal (SPPP) - Established coding conventions, branching strategy. - Completed Lab1 and ReadMe. - Setup a default PR template. | 1. Faced minor environment setup issues 2. Unfamiliarity with some technical frameworks/tools | 1. Initial issues with scheduling, but quickly resolved. 2. Finding tools to help with Agile management. 3. One team member dropped class. 4. Onboarded new team member. | 1. Researching tools/familiarizing them. 2. Communicating on unfamiliar topics. | N/A | N/A | N/A | N/A | N/A | 70.5 | 59.5 | 11 | 19 | 8 | 0 | 2 | 0 | 17 | 8.5 | N/A
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
James Rose
Pedro Ramirez
Stacey Burns
Qi Chen
Gopi Rayini
Yongxiang Chen

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## James Rose
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/11 | 14.5 | 11.5 | 3 | 0 - Learn GitHub, React, Jiro, and front-end coding in general 1 - Trying to remember what needs to be done each week and what assignments need to be done this week 5 - Team meetings regarding the project plan and outline 6 - Learning all the systems and getting used to the new environments | 8 | 1 |  |  |  | 3 | 2 | 0.5 | Used ChatGPT to look for the best project management tool for our team. Also used ChatGPT to better understand some of the unknown web applications and frontend coding terms. | 1. Participated in group meetings 2. Contributed to writing sections of SPPP 3. Helped choose which project management tool to use | 1. Not familiar with front-end coding at all, or some of the frameworks we've been discussing to use. 2. Wasn't quite sure what my role was and what I should be doing to help the team in the planning phase, especially when not understanding front-end. | 1. Been watching a lot of YouTube regarding front-end software and the React framework, the framework Pedro decided on. 2. Going to discuss what I could do to support the team. Going to offer to do the team SPPP for the team each week. | 0 - continue to learn react, typescript, bootstrap, and front-end coding in general 10 - begin completing tasks assigned by Pedro 1- Fill out accomplishment summary for team and myself | 11

## Pedro Ramirez
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/11 | 17 | 17 |  | 0 - learn git and GitHub 1 - create app design, road map and requirements, 5 - make project plan 6 - set up git and the project 7 - prepare presentation to team | 2 | 6 |  |  |  | 5 | 2 | 2 | Use ChatGPT to research the implementation and requirements | write the design and implementation details and created a road map to build the app | I was diffucult to set the Jira project | issue has been solved | Initialize React + TypeScript project and install all dependencies (Bootstrap). Set up a component library (buttons, layout, header, etc.). Build login/register components. | 25-30

## Gopi Rayini
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/11 | 11.5 | 8.5 | 3 | 0 - learn git, GitHub, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  | 2 |  | 1 | 1 | 0.5 | Use chatgpt to research branching, configuration tools, and elicitate some high level requirements, which we discussed in the team meeting. | 1. Helped with several sections of SPPP 2. Setup local git and committed to lab1, adding a PR template, and submitting the required deliverables for the week. 3. Initialized springboot project. 4. Participate in Iteration 0 presentation | 1. Getting used to communication styles and frequency. 2. Gap in technical familiarity related to frameworkd, config tools, etc. | 1. Scheduled regular meetings and delegated tasks according to roles. 2. Use AI to find tools and help set them up and familiarize. | 0 - continue to setup Springboot 1 - start Sprint 1 and tasks related 3 - implement boiler plate code using Java 6 - setup GitHub Actions pipeline 6 - setup the Docker environment 2 - define the UML for classes | 12

## Qi Chen
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/11 | 9 | 7 | 2 | 0 - learn git and atlassian 5 - group meeting 6 - set up the environment 7 - search previous related projects | 1 |  |  |  |  | 3 | 1 | 2 |  | 1. Prepare project draft and ideas 2. Set up git, commit a test message on git | 1. not familar with git and atlassian 2. to-do-list not clear | 1. finish related tutorials 2. ensure project requirements | 0 - continue to learn git and atlassian 1 - continue to define requirements 2 - start project design | 10
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0

## Yongxiang Chen
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/11 | 8 | 8 | 0 | 0 - Learn Git and GitHub, and watch tutorials on Jira, Azure, and ClickUp. 5 - Explain why I joined late and show that I have understood the current division of tasks and the work I need to do. 6 - Set up Git, create accounts for Jira, Azure, and ClickUp. 7- Go through the team documents inside the Goolge Drive. | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | Use ChatGPT to help me solve problems when learning Git. | Set up Git, clone the project and finished lab1. | 1. I joined the team late, so it took me a lot of time to catch up on what we were doing. 2. I am completely new to Git, GitHub, Jira, Azure, and ClickUp, so I need to watch tutorials to become familiar with them. | 1. Stay in touch with my teammates. 2. Continue studying the applications I am not yet familiar with. | 0 – Continue learning Git and GitHub, and review my knowledge of Java, JavaScript, and databases. 5 – Attend meetings to discuss the project and stay in touch with teammates to clarify which part I should mainly focus on. | 10

## Stacey
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/11 | 10.5 | 7.5 | 3 | 6 - Clone project in GitHub 5 - Complete Risk Management _SPPP 5 - Set up JIRA board 5 - Take meeting minutes 0 - Review deliverables 7 - Assist with powerpoint 7 - Iteration 0 presentation 6 - Peer Review | 1 |  |  |  |  | 4 | 1.5 | 1 | Used copilot to help refine QA requirements for SPPP. It was helpful as it took the input I gave it and broke it down into smaller, more understandable components which I did use. Also used it for the Risk Management SPPP to refine answers. | 1. Refine QA section of _SPPP doc 2. Clone project from GitHub 3. Participate in Iteration 0 presentation 4. Complete Risk Management SPPP 5. Help team complete _SPPP | 1. Unclear as to what I can do next to help get the project moving | 1. Will discuss with the team on Discord and during our meeting on Wednesday | 0 - Help with requirements/user stories 1 - Start to set up selenium framework 3 - Start taking on user stories/tasks to help build code | 10