## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/7 - 9/11 | - Set up project repository with version control (GitHub) - Drafted the Software Project Plan Proposal (SPPP) - Established coding conventions, branching strategy. - Completed Lab1 and ReadMe. - Setup a default PR template. | 1. Faced minor environment setup issues 2. Unfamiliarity with some technical frameworks/tools | 1. Initial issues with scheduling, but quickly resolved. 2. Finding tools to help with Agile management. 3. One team member dropped class. 4. Onboarded new team member. | 1. Researching tools/familiarizing them. 2. Communicating on unfamiliar topics. | N/A | N/A | N/A | N/A | N/A | 73.5 | 61.5 | 12 | 24 | 8 | 0 | 2 | 0 | 17 | 8.5 | N/A
1 | 9/12 - 9/23 | - Setup AWS EC2, ECR, and RDS - Setup 2 CI/CD workflows in GitHub - Added APIs for user creation and login - Added APIs for saving/retreiving jobs - Added JWT authorization - Added aside components with filters - Added theme button - API Integration - Added JobsView with JobCard components - Integrated Layout Components into Main App | 1. Issues with docker container deploying to the ec2 instance. 2. Some PRs were merged with breaking code 3. PRs with credentials included | 1. One team member didnt have a computer for a short period | N/A | 56 | 28 | 1 | 1 | 0 | 267 | 249 | 18 | 18 | 14 | 47.5 | 74 | 32 | 17.5 | 29.5
2 | 9/24 - 10/7 | - Implemented error handling and response standardization - Set up Postman collection for API testing - Test Suite for Auth (Login/Registration), MyJobs (Saved/Applied), and 401/404 (Jest framework) - Fetched and managed MyJobs (Saved & Applied) - Collaborated with frontend for API integrations - Refactored and clean up code to fit UML design - Fixed and enabled unit tests - Added testing to the frontend - Set up Selenium Framework - Connected frontend to backend (Login, Register, and Content/Jobs) | 1. Backend container crash: missing JWT secret 2. Deploy/config issue: failing health endpoint 3. Infra issue: EC2 disk filled with old Docker images (~17 images), breaking deployments until pruned | N/A | N/A | 64 | 3 | 0 | 0 | 0 | 226 | 213 | 13 | 11 | 9 | 26.5 | 72 | 49 | 17 | 12
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
James Rose | Management Plan |  | Database Design | Added majority of information regarding frontend testing. | Iteration 2 Presentation | Build login/register components. Built the Aside portion of both the home page and the MyJobs page. Created buttons for Saved Jobs and Applied Jobs as well as delete features for both. | Built test cases for classes such as RegisterForm.tsx, Aside.tsx, Field.tsx, MyJobsButton.tsx, and validation.ts | Helping to fix issues with mobile version | Being active on Discord as well as practive with stories on jira. Weekly meetings with whole team and or frontend team.
Pedro Ramirez |  | design all front end requirements | Design app interface | Create README file initial state | created video presentation for iteration 1 | Created the app skeleton and dependencies, also built the jobsLists page and incorporated the public API to fetch the jobs, and reviewed pull requests Connect the backend endpoints to the front-end, fix bugs from different pull requests, and incorporate React router to display every page properly. Improve UI design and implement CSS enhancements | Create test cases to test the login and registration components |  | Create stories and tasks in Jira and divide responsibilities
Stacey Burns | Update related work section, Code Commit Guideline and Git Branching Strategy section, CI/CD plan, and timeline | Assisted with drafting some JIRA tickets for work we did last week | UML Class Diagram and Security portion of _SDD doc | Testing Summary, automated testing report, and testing metrics section for the backend | Iteration 0 presentation | Configure Spring Security and JWT filters, reconfigure to match endpoints for auth login and register | Unit tests in security folder (JwtUtilTest and SecurityIntegration). Started setting up selenium framework. Setup Postman Collection for API verification for tokens. | Trying to help with issues we are seeing with our configs when we run our containers. Originally ran into issues with jwt secret not being found, but now currently running into some DB issues. Actively debugging. | Communicating via Discord with team. Meeting at least once a week to discuss status and next steps.
Qi Chen |  | Created tickets for lab2; Assisted in managing and finishing some tickets in JIRA. | backend architecture; drafted all database fields | Manual testing report for backend | Iteration 1 presentation and video | Job related APIs Database configuration General request/response boxing and global API logging. | Database connection testing | Database initialization configuration | Communicated via Discord. Participated in team meeting for future plans. Acted as the minute taker during the 3rd meeting.
Gopi Rayini | Configuration Section |  | Design Patterns, REST APIs |  | Iteration 0 video and contribution towards ppt |  |  | Created AWS RDS database, EC2 instance, ECR, GitHub Workflows, SAST code scanning | Communicated via Discord. Participated in team meeting for future plans. Connecting with team members for preparing and recording presentations.
Yongxiang Chen |  |  | Introduction, Business Logic and key algorithms |  | Iteration 2 Presentation | Create styles files, create header, footer, buttons components | Wrote Jest tests (Auth, MyJobs, 401/404). | Enhance the UI design | Communicate via Discord with team and front end team. Regular weekly meeting. Connecting with James to design the slides of presentation and the demo

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## James Rose
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/11 | 16.5 | 13.5 | 3 | 0 - Learn GitHub, React, Jiro, and front-end coding in general 1 - Trying to remember what needs to be done each week and what assignments need to be done this week 5 - Team meetings regarding the project plan and outline 6 - Learning all the systems and getting used to the new environments | 12 | 1 |  |  |  | 3 | 2 | 0.5 | Used ChatGPT to look for the best project management tool for our team. Also used ChatGPT to better understand some of the unknown web applications and frontend coding terms. | 1. Participated in group meetings 2. Contributed to writing sections of SPPP 3. Helped choose which project management tool to use | 1. Not familiar with front-end coding at all, or some of the frameworks we've been discussing to use. 2. Wasn't quite sure what my role was and what I should be doing to help the team in the planning phase, especially when not understanding front-end. | 1. Been watching a lot of YouTube regarding front-end software and the React framework, the framework Pedro decided on. 2. Going to discuss what I could do to support the team. Going to offer to do the team SPPP for the team each week. | 0 - continue to learn react, typescript, bootstrap, and front-end coding in general 10 - begin completing tasks assigned by Pedro 1- Fill out accomplishment summary for team and myself | 11
2 | 09/12-9/23 | 19 | 18 | 1 | 0 - Read up on Github, Docker, and frontend coding 1 - Understanding what is expected in each pull request and what is needed from a code stand-point 2 - Going through a class diagram and insuring the code I'm writing is clear and efficient and does not step on anyone elses toes. 3 - Writing the code for LoginForm, Register Form, index, and validation. 4 - Ensured system runs and is navigable on Vite. Will be easier to stress test once theres a place to go after logging in or registering. 5 - Attended meetings and discussed details on the next sprint. Also discussed short comings and things to work on regarding the previous sprint. 6 - Set up my own system from the Docker Pedro set up. 7 - | 4 | 2 | 1 | 6 | 2 | 1 | 5 |  | Used ChatGPT to decide class strucuture within the Login and Register screens on the frontend. Also checked my code for errors and efficiency. AI was used to write parts of the tasks in the Icebox. Also used AI to help me navigate Docker. | 1. Completed RegisterForm, LoginForm, index, and verification classes for the app. These are the interfaces for logging in and registering for the app. 2. Created pull requests for each of child task and assigned it to Pedro to check. | 1. Unfamiliar with Docker and was having trouble launching it on my computer. 2. Unfamiliar with pull requests and the Github, Visual Studio Code relationship. 3. Was not sure what documents in Google Drive was every week or once a semester. | 1. Got Docker to work on a different laptop and began to familiarize myself with it. 2. Was able to create pull requests for each of my child tasks under different branches (at first was trying to create multiple pull requests from a single branch). 3. Have consulted with my team about the documets in the Google Drive and am now more familiar with thier timelines. | 2 - Create parent and child tasks for Team B (frontend) and post them on jira. Trying to help out Pedro who has done a lot of the work upfront. 8 - Complete my parent class and create pull requests for Pedro to check. 1- Fill out Progress Report for myself and my team | 11
| 09/24 - 10/7 | 35 | 34.5 | 0.5 | 0 - Jest tesing 1 - Going over lab and personal sprint 2 - Brainstorming testing structure and what was of the highest priority 3 - Writing the code for MyJobsButton. Created applications for saved jobs and applied jobs buttons. Created delete features for said categories and more. 4 - Tests on Aside.tsx, Field.tsx, LoginForm.tsx, RegisterForm.tsx, MyJobsButton.tsx, and validation.ts 5 - Filled out frontend information for the STD document and Group Iteration Progress for Progress Report. Attended meetings and discussed details on the next sprint. Also discussed testing goals and frontend, backend connection. 6 - Getting jest to run and efficiently execute tests | 1 | 1 | 1 | 15 | 14 | 1 | 2 |  | Used chatgpt to help write tests. Also used VSC Copilot to help fix json files. | 1. Made some big additions to the STD document. 2. Implement a MyJobs page with a toggle button for saved and applied jobs list. 3. Implemented delete all, and delete single, options with buttons. | 1. Json files were not working for me inititially. | 1. Pedro recommended I use the Copilot feature in VSC which after some fenagaling worked to correct the package.json file. | 3 - Add more testing 4- Spend time debugging and improving UI | 7

## Pedro Ramirez
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/08 | 18 | 17 | 1 | 0 - learn git and GitHub 1 - create app oad map and requirements, 5 - make project plan 6 - set up git and the project 7 - prepare presentation to team | 2 | 6 |  |  |  | 5 | 2 | 2 | Use ChatGPT to research the implementation and requirements | 1. Wrote the design and implementation details 2. Created a road map to build the app | 1. I was diffucult to set the Jira project | issue has been solved | Initialize React + TypeScript project and install all dependencies (Bootstrap). Set up a component library (buttons, layout, header, etc.). Build login/register components. | 16-20
2 | 09/09-09/15 | 19 | 18 | 1 | 0 - Learned Docker 1 - Defined app architecture 2 - Created and designed the app's folder skeleton 3 - incorporated all dependencies into the React project 5 - Created stories and divided front-end Jira tickets 7 - Reviewed teammates' pull requests | 2 | 2 | 4 | 1 |  | 5 |  | 4 | Use ChatGPT to research the implementation and requirements and copilot for code creation | 1. Bootstrap the app with all the dependencies and organize the app's folders 2. Created the first Jira sprint, assigning tickets to the team 3. Reviewed and gave feedback to the team's pull requests | 1. pull requests conflicts when trying to merge to the dev branch | 1. I taught team mates how to create branches to have the latest dev branch copy from GitHub | 1. Build the rest of the components and call the public Job's API 2. Create main pages and add React Router 3. Enhance design | 20-25
3 | 09/16-09/22 | 20 | 19 | 1 | 0 - Learned React Router 1 - Defined main components 2 - Designed components hierarchy 3 - Created JobCard and JobList components and integrated Jobs API 5 - Created stories and divided front-end Jira tickets 7 - Reviewed teammates' pull requests | 2 | 1 | 1 | 6 |  | 4 |  | 5 | Used copilot for code generation, and ChatGTP for bugs | 1. Taught teammates how to work using components 2. Created the second Jira sprint, assigning tickets to the team 3. Built several components into the project and wrote code to fetch the data from the API 4. Reviewed pull requests and gave feedback on the team's pull requests 5. Created iteration 1 presentation video, and worked on some deliverables | 1. bugs in all pull requests | ChatGTP help to solve all issues and finalize iteration 1 | 1.Implement “My Jobs” dashboard (saved + applied jobs). 2. Hook UI to real backend. 3. Add login/logout integration with JWT. | 18-24
4 | 09/23-09/29 | 19 | 18 | 1 | 0 - Learned React router 2 - Defined logic to save, apply, and delete jobs 3 - Connect the back end to the front end for the login and registration components 5 - Created stories and divided front-end Jira tickets 7 - Reviewed teammates' pull requests | 2 | 2 |  | 10 |  | 2 |  | 2 | Mostly Copilot for coding and finding bugs, ChatGTP for creating the user stories | 1. Define the front flow logic design and implementation 2. Created the third Jira sprint, assigning tickets to the team 3. Revised a few components into the project and connected the login and registration backend endpoints to the front end 4. Reviewed pull requests and gave feedback on the team's pull requests | I couldn't connect the endpoints to the login component, a 401 error appeared | Copilot help me inspect the backend to properly pass the expected body | 1. Connect the rest of the endpoints 2. Create more tests 3. Create some 401 and 404 components 4. Fix some of the UI design | 20 -25
5 | 09/30-10/06 | 23 | 22 | 1 | 0 - Learned Jest 2 - Defined the rest of the design or UI 3 - Connect the rest of the endpoints to the front-end and change the design using CSS 5 - Created stories and divided front-end Jira tickets 7 - Reviewed teammates' pull requests | 3 |  | 2 | 14 |  | 2 |  | 1 | Copilot helped connect the front with the back and ChatGTP for Jira's tickets | 1. Define the final front design 2. Created the four Jira sprint, assigning tickets to the team 3. Fully connect all endpoints to connect the back with the front properly. 4. enhanced the UI using CSS and incorporated the 404 error page 4. Reviewed pull requests and gave feedback on the team's pull requests | different errors from the backend when trying to connect the endpoints: 401, 404, 500, and CORS errors | Copilot help me inspect the backend to properly pass the expected body and token | 1. Create the CI/CD pipeline 2. more tests to enhance code 3. fix the mobile version (front end) 4. fix last bugs | 20-25

## Gopi Rayini
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/11 | 11.5 | 8.5 | 3 | 0 - learn git, GitHub, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  | 2 |  | 1 | 1 | 0.5 | Use chatgpt to research branching, configuration tools, and elicitate some high level requirements, which we discussed in the team meeting. | 1. Helped with several sections of SPPP 2. Setup local git and committed to lab1, adding a PR template, and submitting the required deliverables for the week. 3. Initialized springboot project. 4. Participate in Iteration 0 presentation | 1. Getting used to communication styles and frequency. 2. Gap in technical familiarity related to frameworkd, config tools, etc. | 1. Scheduled regular meetings and delegated tasks according to roles. 2. Use AI to find tools and help set them up and familiarize. | 0 - continue to setup Springboot 1 - start Sprint 1 and tasks related 3 - implement boiler plate code using Java 6 - setup GitHub Actions pipeline 6 - setup the Docker environment 2 - define the UML for classes | 12
2 | 09/10-09/16 | 19 | 16 | 3 | 0 - Learn AWS and GitHub Workflows 1 - Review configuration section of SPPP 2 - 4 - test functionality in localhost 5 - meet with teammates to clarify deliverables 6 - setup secrets and envrionmental variables needed for workflows | 1 | 2 | 1 | 8 |  | 1 | 3 |  | ChatGPT - Researching places to deploy containers, building worklfows, genery inquiry for configuration | 1. Update SPPP 2. complete lab2 and implement dockerfile and other workflows | 1. setting up IAM roles and appropriate permissions in AWS 2. configuring the PEM file and access to DB from local | 1. resolved after researching throught chatgpt 2. resolved after further research | 0 - Semgrep and CodeQL scanning for SAST 1 - Update SDD 2 - Add new controllers according to previous designs 3 - push authentication apis to dev 6 - setup secrets | 20
3 | 09/17-09/23 | 26 | 23 | 3 | 0 - Semgrep and CodeQL scanning for SAST 1 - Update SDD 2 - Add new controllers according to previous designs 3 - push authentication apis to dev 4 - test functionality in localhost 5 - meet with teammates to clarify deliverables 6 - setup secrets and envrionmental variables needed for workflows | 2 | 2 | 3 | 10 | 2 | 1 | 3 | 0 | ChatGPT - Generating code for workflows, updating documentation, debugging code issues | 1. Update SDD 2. help teammates finalize the PRs to merge into dev 3. merge the finalized dev code to main branch and create a release | 1. correcting PR that exposed credentials 2. fixing incorrect dependencies in POM file | 1. resolved in a commit 2. resolved in commit | 0 - Unit Testing 1 - Update SDD SPPP 2 - Add new controllers according to previous designs 4 - test functionality in localhost 5 - meet with teammates to clarify deliverables | 25
4 | 09/24-9/30 | 19 | 16 | 3 | 1 - Analyze SDD and create user stories 2 - Research design patterns for package structure 3 - Refactor code using a more vertical design pattern 4 - Test code in local and using GH workflow 5 - Attend team meetings, collaborate to resolve issues in discord chat 6 - Edit Dockerfile and Deploy YML to accommodate for updates | 0 | 1 | 3 | 5 | 3 | 1 | 3 | 0 | ChatGPT - Generating code for workflows, updating documentation, debugging code issues | 1. Update Progress report 2. Update SDD | N/A | N/A | 1 - Analyze SDD and create user stories 2 - Research design patterns for package structure 3 - Refactor code using a more vertical design pattern 4 - Test code in local and using GH workflow 5 - Attend team meetings, collaborate to resolve issues in discord chat 6 - Edit Dockerfile and Deploy YML to accommodate for updates | 20
5 | 10/01-10/07 | 19 | 16 | 3 | 1 - Analyze SDD and create user stories 2 - Research design patterns for package structure 3 - Refactor code using a more vertical design pattern 4 - Test code in local and using GH workflow 5 - Attend team meetings, collaborate to resolve issues in discord chat 6 - Edit Dockerfile and Deploy YML to accommodate for updates | 0 | 1 | 0 | 3 | 5 | 2 | 5 | 0 | ChatGPT - Generating code for workflows, updating documentation, debugging code issues | 1. Update Progress report 2. Finalize all files and submit | 1. Docker container is failing to run and restarting continuously | 1. Still open, working on debugging issue | 1 - Review final requirements 3 - Add/Fix API endpoint functionality 4 - Finalize tests 5 - Communicate final iteration tasks | 20
6

## Qi Chen
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/09 | 9 | 7 | 2 | 0 - learn git and atlassian 5 - group meeting 6 - set up the environment 7 - search previous related projects | 1 |  |  |  |  | 3 | 1 | 2 |  | 1. Prepare project draft and ideas 2. Set up git, commit a test message on git | 1. not familar with git and atlassian 2. to-do-list not clear | 1. finish related tutorials 2. ensure project requirements | 0 - continue to learn git and atlassian 1 - continue to define requirements 2 - start project design | 10
2 | 09/10-9/16 | 27 | 23 | 4 | 0 - learn mysql setup 1 - Write user stories and acceptance tests 2 - Design database schema 3 - Implement database setup code and configuration 4 - Implement database connection tests 5 - group meeting 6 - setup the development environment and docker 7 - research on related projects 7 - Drafted iteration 1 presentation slides Related github PRs: https://github.com/BUMETCS673/CS673OLFall25_team2/pull/15 https://github.com/BUMETCS673/CS673OLFall25_team2/pull/21 | 2 | 1 | 2 | 2 | 8 | 1 | 4 | 3 | GPT assisted for database initialization implementation. | 1. Implemented database connection code and tests. |  |  | 1. Finiish assigned user functions. | 20
3 | 09/17-9/23 | 24 | 23 | 1 | 0 - learn postman setup 1- Define a global exception handler in Spring Boot 2 - Create a common API response format 3 - Implement error handling and response standardization and logging 3 - Implement job related APIs 4 - Write tests to validate error cases 5 - group meeting 6 - setup the postman 7 - research on related projects 7 - finished iteration 1 presentation slides and video Related PR: https://github.com/BUMETCS673/CS673OLFall25_team2/pull/38 | 1 | 1 | 3 | 8 | 2 | 1 | 4 | 3 |  | 1. Implement error handling and response standardization 2. Iteration1 slides and presentation | 1. some testing problems |  | 1. Finiish assigned user functions. | 15
4 | 09/24-9/30 | 11 | 10 | 1 | 0 - learn connect frontend and backend 1 - ensure data fields 4 - test endpoints 5 - chat and group meeting 7 - look through related materials Related PR: https://github.com/BUMETCS673/CS673OLFall25_team2/pull/57 | 1 | 1 | 0 | 0 | 2 | 5 | 0 | 1 |  | 1.finish backend code related to frontend 2. overall testing |  | 1.promote some code 2. overall testing | 1.prepare for iteration2&3 | 20
5 | 10/01-10/07 | 10 | 9 | 1 | 0 - learn connect frontend and backend 4 - test endpoints 5 - chat and group meeting 7 - look through related materials | 2 | 0 | 0 | 0 | 5 | 1 | 0 | 1 |  | 1.finish backend code related to frontend 2. overall testing |  | 1.promote some code 2. overall testing | 1.prepare for iteration3 | 15
6 |  | 0 | 0

## Yongxiang Chen
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/11 | 8 | 8 | 0 | 0 - Learn Git and GitHub, and watch tutorials on Jira, Azure, and ClickUp. 5 - Explain why I joined late and show that I have understood the current division of tasks and the work I need to do. 6 - Set up Git, create accounts for Jira, Azure, and ClickUp. 7- Go through the team documents inside the Goolge Drive. | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | Use ChatGPT to help me solve problems when learning Git. | Set up Git, clone the project and finished lab1. | 1. I joined the team late, so it took me a lot of time to catch up on what we were doing. 2. I am completely new to Git, GitHub, Jira, Azure, and ClickUp, so I need to watch tutorials to become familiar with them. | 1. Stay in touch with my teammates. 2. Continue studying the applications I am not yet familiar with. | 0 – Continue learning Git and GitHub, and review my knowledge of Java, JavaScript, and databases. 5 – Attend meetings to discuss the project and stay in touch with teammates to clarify which part I should mainly focus on. | 10
2 | 09/10-09/16 | 20 | 19 | 1 | 0 - Learn push, revert a commit and bootstrap 2 - Create style files, header, footer, and button components 4 - Test each buttons' function 5 - Goup meeting | 2 | 0 | 15 | 0 | 2 | 1 | 0 | 0 | Ask ChatGPT how to send pull request and how to revert a pull request. Also asked help for design the buttons. | Design the components of UI | 1. not familiar with Docker, and git 2. still need to learn more knowledge of front end. | 1. Keeping learning skills of web application 2. Asking question when facing a problem | 0 - Keeping learning skills from internent or teamates 2 - UI design 5 - Group meeting | 20
3 | 09/17-09/23 | 21.5 | 20 | 1.5 | 0 - Learn how to properly create a pull request 2 - Integrate header, footer, and ehance the UI design 4 - Test the UI design 5 - Goup meeting and forntend-team meeting | 0.5 | 0 | 12.5 | 7 | 0 | 1.5 | 0 | 0 | Use ChatGPT to help me with UI design, including how to move components and which colors harmonize well together. Help me with SDD document. | Write 2 sectons of SDD | 1. not familar with the UI desgn | 1. Ask questions when needed and communicate timely. | 0 - Learn UI design 4 - Front end testing 5 - Team meeting | 20
4 | 09/24-09/30 | 18 | 18 | 0 | 0 - Studied TDD/BDD concepts 2 - Designed test cases for REST API endpoints 4 - Wrote Jest tests (Auth, MyJobs, 401/404). 5 - Communicated with teammates | 1.5 | 0 | 3 | 0 | 13 | 0.5 | 0 | 0 | Generated Jest test code and testing ideas | Write Jest tests for Login, Registration, 401/404... | 1. not familar with Jest tests | 1. Keep learning 2. Ask teammates for help if need help. | 0 - Learn Jest Tests 4 - Test Front end and Back end 5 - Team meeting | 20
5 | 10/1 - 10/7 | 10 | 9.5 | 0.5 | 2 - Write STD and presentaion slides, dub the demo, record presentation 5 - Communicated with presentation teammates, weekly meeting | 0 | 0 | 8 | 0 | 0 | 2 | 0 | 0 | Use ChatGPT to generate some bullets for presentation | 1. Write some of the frontend part STD, and some parts fo the slids 2. Dub the demo and edit the presentation video | No issuses this week | Next week I will add more tests | 0 - Learn to write unit tests 5 - Team meeting | 10

## Stacey
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/07-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/11 | 10.5 | 7.5 | 3 | 6 - Clone project in GitHub 5 - Complete Risk Management _SPPP 5 - Set up JIRA board 5 - Take meeting minutes 0 - Review deliverables 7 - Assist with powerpoint 7 - Iteration 0 presentation 6 - Peer Review | 1 |  |  |  |  | 4 | 1.5 | 1 | Used copilot to help refine QA requirements for SPPP. It was helpful as it took the input I gave it and broke it down into smaller, more understandable components which I did use. Also used it for the Risk Management SPPP to refine answers. | 1. Refine QA section of _SPPP doc 2. Clone project from GitHub 3. Participate in Iteration 0 presentation 4. Complete Risk Management SPPP 5. Help team complete _SPPP | 1. Unclear as to what I can do next to help get the project moving | 1. Will discuss with the team on Discord and during our meeting on Wednesday | 0 - Help with requirements/user stories 1 - Start to set up selenium framework 3 - Start taking on user stories/tasks to help build code | 10
2 | 09/11-09/16 | 17 | 16.5 | 0.5 | 1 - Write User Stories 3- Peer Review 2- UML Diagram 0- Research and Test Rise API 6- Research and Install Docker 6- Run local dev environment 6- Start setting up selenium framework and writing tests | 0.5 | 2 | 4 | 1.5 |  |  | 8.5 |  | Used copilot to help refine user stories, to help debug issues with deploying. It did prove to be helpful as it found the reason the deployment was failing. For the user stories, I didn't love all of the feedback, but I did use some of the child tasks it provided. | 1. Drafting User Stories 2. Drafting class UML diagram 3. Started selenium framework 4. Peer Reviewed code 5. Got local dev working to start building code | 1. Issues with deployment that team ran into 2. Issues with getting dev to build and run locally | 1. Resolved 2. Resolved | 3 - Implement User Authentication 4 - Set up Postman Collection for API testing | 15-20
3 | 09/17-09/22 | 19.5 | 19 | 0.5 | 3 - Configure Spring Security and JWT filters 4- Setup Postman Collection for API verification 7- UML Class Diagram and Security portion of _SDD doc 7- Update Risk Management document 7- Update related work section, Code Commit Guideline and Git Branching Strategy section, CI/CD plan, and timeline 4- Raise PR to implement selenium framework 7- Update testing summary, automated testing report, and testing metrics section of the _SDD document |  |  |  | 9.5 | 2 |  |  | 7.5 | Used ChatGPT to figure out where to begin with implementing user authentication. Yes, it was very helpful. I ended up using a lot of AI's suggestions for the implementation, but needed to bend it to what the project already had implemented. | 1. Assist with application by building user authentication 2. Set up postman collection and test for tokens and secure endpoints with instructions for other team members 3. Assisted with the security design and UML diagram for the _SDD document 4. Updated risk management document 5. Updated _SPPP sections that we received constructive feedback on 6. Updated _STD sections based on current tests we have | 1. It's becoming a bit more challenging with communicating and holding meetings for all team members as schedules aren't always aligned 2. Secure details were merged in a PR for our database. Issues with peer reviews and catching these things before merging. | 1. We are doing our best to stay in contact over Discord. Other team members have taken the role of trying to coordinate or see when our next team meeting will be. 2. A PR to resolve has been raised by another team member | 3 - Help with extending REST APIs for saving, applying, and deleting jobs OR 3 - Help with database persistence for saved/applied jobs 4 - Continue with building selenium tests | 15-20
4 | 09/23-09/30 | 13 | 12.5 | 0.5 | 4 - Create and fix unit tests 3 - Add appropriate endpoints to login auth and register authentication 4 - Resolve conflicts for selenium framework PR 3 - Peer Review |  |  |  | 1.5 | 11 |  |  |  | Used ChatGPT to help with resolving issues we were seeing with unit tests. Yes, it was very helpful and I ended up using some of the suggested test cases for my unit tests. I did need to adapt slightly and inform ChatGPT of what was already implemented to reduce duplication. | 1. Fixed the unit tests that were failing on dev during each build. No longer need to skip unit tests on the build 2. Added more unit tests around the jwt authentication 3. Changed the auth and register authentication endpoints to match what the front end was using. Needed to update how we are storing names, usernames, and what is needed to register a user. 4. Updated PR for selenium framework. 5. Peer reviewed code | 1. It would have been easier and smoother if front end and back end were aligned earlier on the build process. We are finding that the backend is expected different things than what the front end expects (ie backend is looking for first name and last name on registration but the front end is providing only name). | 1. The backend is going to accommodate the front end. We will refactor based on the json body our APIs receive for registration and login. | 4 - Help with testing 3 - Help with any issues that might arise when we connect the backend to the frontend 3 - Help with code refactoring as needed | 2025-10-15
5 | 9/30-10/07 | 8 | 7.5 | 0.5 | 3 - Fix/Look into issue with EC2 instance to. Caused by: java.nio.file.NoSuchFileException: /home/spring/.jwt-secret. 3 - Fix/Look into issue with database connection through docker 7 - Updated risk management 7 - Updated STD documentation with number of tests and screenshots 7 - Updated SPPP documentation based on feedback - CI/CD, timeline, and related work |  |  |  | 6 |  |  |  | 1.5 | Used ChatGPT to help figure out what I was missing with the EC2 instance. I set up our jwt secret for dev, but did not resolve it for our prod instance. Yes, it was helpful, but I'm still debugging trying to figure out if the fix worked or not. I need some help from my teammates. | 1. Assisted with fixing the issue with the EC2 instance caused by .jwt-secret. 2. Updated risk management document for Iteration 2 submission 3. Updated STD document for Iteration 2 submission 4. Updated SPPP document based on feedback | 1. We are running into issues with our EC2 instance. 2. Communication is getting worse it seems and it is harder to work as a team. | 1. Will reach out to Gopi for help regarding the issue with the EC2 instance. 2. Doing my best to stay in contact over discord. I keep reaching out for help when needed and will continue doing so. | 4 - Help with final end to end testing 3 - Help with any issues that might arise 3 - Help with code refactoring as needed | 2025-10-15