## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 5 | 3 | 3 | 1*3*3=9 | All team members | 2025-09-21 | Redefine the project scope if necessary, and assign the tasks to other team members. | 1 person has dropped the class so far. We have gone pass the add/drop period so I have marked this as resolved. | Closed
| add new team members | One or more team members are added to the group | 5 | 1 | 1 | 1*5*1=5 | All team members | 2025-09-21 | Reassign tasks as needed and onboard new team member | 1 person has joined the group. We have gone pass the add/drop period so I have marked this as resolved. | Closed
| Lack of motivation or responsibility | Team members do not participate or deliver on expected action items and therefore not contributing effectively | 1 | 5 | 4 | 5*1*4=20 | All team members | 2025-10-20 | Try to remind folks, encourage accountability, and assign tasks to other team members if needed | No issues as of yet | Open
Communication | duplicate work | Team members work on the same piece of code or deliverable | 2 | 3 | 3 | 4*3*3=36 | Team leader and all team members | 2025-10-20 | Ensure each team member has their own JIRA task to work on. Ensure communication is happening often so everyone knows what people are working on. Check in via stand up ceremonies. | At the beginning of building code, there was 1 instance of duplication of work. The team members discussed how whoever is assigned the JIRA task should work on that task solely and to reach out if there are any questi | Open
| worked on wrong components | Two or more team members work on the wrong component | 2 | 3 | 3 | 4*3*3=36 | Team leader and all team members | 2025-10-20 | Clarify responsibilities, validate task assignments early, maintain a clear feature list to work on | No issues as of yet | Open
| useless work | One or more team members work on a piece of code that is not used or applied to our application or deliverable | 1 | 3 | 4 | 5*3*4=60 | Team leader and all team members | 2025-10-20 | Clarify responsibilities, validate task assignments early, maintain a clear feature list to work on | No issues as of yet | Open
Requirements | unclear requirements | Requirements are not clear in what the expected deliverable is | 2 | 3 | 4 | 4*3*4=48 | Team leader and all team members | 2025-10-20 | Ensure that all requirements are clear. If there are any questions around the requirements for each component, it should be raised. | Went through functional and nonfunctional requirements as a team. Will use JIRA to document features to be built with detailed description of requirements. No issues as of yet. | Open
| scope creep | We start adding in additional functionality that we did not plan for at the beginning | 2 | 4 | 4 | 4*2*4=32 | Team leader and all team members | 2025-10-20 | Ensure we stick to the MVP plan and that we plan for the appropriate amount of work and person hours needed to complete | No issues as of yet | Open
| constant requirements changes | We start building different components, but then requirements evolve after implementation begins | 2 | 3 | 3 | 4*3*3=36 | Team leader and all team members | 2025-10-20 | Ensure we have all requirements documented and finalized before we start building a component | Had a small issue around different expectations with API endpoints between backend and frontend. Need to ensure we are aligned here. | Open
Management | improper task assignments | One or more team members take on a task they are not able to complete | 2 | 4 | 5 | 4*2*5=40 | Team leader and all team members | 2025-10-20 | Ensure everyone is comfortable with the tasks they are taking on. If issues arise as we go, be sure to make the team aware so we can redirect tasks as needed. | No issues as of yet | Open
| improper planning/time management | As a team, we do not plan appropriately for each iteration - either over or under delivering | 2 | 4 | 3 | 4*2*3=24 | Team leader and all team members | 2025-10-20 | Ensure each team member is aware of the plan for each iteration and tasks are delegated accordingly. Work in sprints with realistic goals. Prioritize building and testing core features first. | Plan to work in sprints with JIRA as a project management tool. Time management has been working well for us so far with breaking down the expectations of each sprint. | Open
Technology competence | Not familiar with the programming language used | One or more team members are not familiar with Java or JS | 5 | 2 | 3 | 1*4*3=12 | Team leader and all team members | 2025-10-06 | Work as a team. Research independently as needed and reach out for help when needed. | Not everyone has experience with Java or JS. Will do some self learning. Everyone is working really well as a team. We rely on our more experienced developers for our PRs and task delegation. We're pretty far into the build at this point so I am marking this as closed as we have all had experience with the technology now. | Closed
| Not familiar with unit testing | One or more team members are not familiar with unit testing | 5 | 2 | 2 | 1*4*2=8 | Team leader and all team members | 2025-10-06 | Research Junit and Jest. Reach out for help when needed. | Not everyone has experience with unit testing. Will do some self learning and provide examples as needed. We're pretty far into the build at this point so I am marking this as closed as we have all had experience with | Closed
Design and implementation | Improper design | Design is not scalable or modular | 3 | 2 | 2 | 3*4*2=24 | Team leader and all team members | 2025-10-20 | Within reason, ensure we are taking scalability into account with our design | No issues as of yet | Open
| Messy or inconsistent code | Codebase lacks consistency or standards | 2 | 4 | 3 | 4*2*3=24 | Team leader and all team members | 2025-10-20 | Implement standards all team members are to follow in the _SPPP and ensure all PRs are reviewed properly. Review code regularly and test as soon as we can. | We are seeing some redundant code or code that is not going to be used. Need to refactor. | Open
| Bugs in job listing functionality | Issues with job postings, viewing, searching, applying to jobs, saving or deleting | 2 | 4 | 5 | 4*2*5=40 | Team leader and all team members | 2025-10-20 | We will be using stubbed data so we reduce the risks associated with having an employer UI as well. Begin testing early and test frequently. Reduce complexity if needed. | No issues as of yet | Open
Testing | Not enough testing | Features and integrations are not adequately tested | 2 | 5 | 4 | 4*1*4=16 | Team leader and all team members | 2025-10-20 | Ensure we begin testing as soon as we are able and prioritize bugs as and when they appear. Write unit tests and implement automated tests along with manual, functional testing. | No issues as of yet | Open
Integration and deployment | Not enough time for integration and deployment | Due to condensed schedule, not enough time to deploy and we run into issues with integration of our front and back end development | 2 | 5 | 5 | 4*1*1=4 | Team leader and all team members | 2025-10-20 | Ensure a well-defined deployment plan is in place. Prioritize early research into CI/CD options. Create a detailed integration strategy for smooth coordination between the UI and backend | Having some issues with running on production. First we had an issue with our jwt secret file and now we are running into issues with connecting to the DB. Actively communicating and debugging with the team on this. | Open
Security | Security with user accounts | Insecure or insufficient implementation of user authentication | 2 | 3 | 3 | 4*3*3=36 | Team leader and all team members | 2025-10-20 | Ensure we build MFA feature and password hashing to help secure authentication | Running into issues with prod finding the secret, but I believe this is resolved. Need to ensure end to end flow works as expected here. | Open